## NUC900BSP_project
Название проекта | Введение | Ответственный | Контакт | Code completion (percentage x%) | Written document (percentage x%) | Срочность
kernel transplantation | Transplant the latest Linux kernel, the main line track linus | 万宗顺 (10000 Shun) | mcuos.com@gmail.com | Completed | Не началась
LCD driver | The preparation of the development board LCD screen NUC950 | 王强(Wang Qiang) | rurality.wq@gmail.com | In progress (90%) | Не началась |  | Срочный
TSC | nuc950 touch screen driver | 王强 | rurality.wq@gmail.com | In progress (0%) | Не началась
SD driver | SD driver write | 李杰（暂定）(Li Jie (предварительно)) | eltshanli@gmail.com | In progress (10%) | Не началась |  | Medium
USB device | Write usbd drive | 待申请 (After the application) |  | Not started | Не началась |  | Несрочный
USB host | Write usbh drive | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась |  | Близко
EMC | NIC driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
GDMA | DMA interface, implementation, strictly speaking, not a driver, mach-w90x900 the following API | 万宗顺 | mcuos.com@gmail.com | In progress (80%) | Не началась
NAND | NAND driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
NOR | NOR | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
SPI | SPI driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
RTC | RTC driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
AUDIO | audio drivers | 万宗顺 | mcuos.com@gmail.com | In progress (0%) | Не началась
2D-engine | 2d-graphic | 待申请 |  | Not started | Не началась
ATAPI | IDE drive | 待申请 |  | Not started | Не началась
UART0 | UART0 Driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
UART1-4 | UART1-4 drive | 待申请 |  | Not started | Не началась
TIMER | TIMER drive | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
AIC | Interrupt Controller | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
GPIO | GPIO | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
I2C | I2C Driver | 李杰 | eltshanli@gmail.com | In progress (90%) | Не началась
watchdog | Watchdog driver | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
PWM | PWM drive | 待申请 |  | Not started | Не началась
keypad | kpi drive | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
PS2 | PS2 driver | 待申请 |  | Not started | Не началась
ADC | TouchScreen FOR nuc910 | 万宗顺 | mcuos.com@gmail.com | Completed | Не началась
clock API | cpu clock interface and add new API, intended to put all the clk-related forms are made of kernel API. | 万宗顺 |  | In progress（90%） | Не началась
cpufreq | Dynamic application interface of FM and | 李杰 (Li Jie) | eltshanli@gmail.com | In the Test of bug, need in-depth debugging. | Не началась
NUC900 Linux mainline BSP BUG tracking | BUG basic testing and tracking, and submit the patch | 李杰 | eltshanli@gmail.com | Ongoing at any time to find bug | Не началась
toolchain-building | Create a new version of the compiler tools | 待申请 |  | Not started | Не началась
Kernel debugging method | Written documentation-how to use KGDB, GDB | 待申请 |  | Not started | Не началась
BSP integration test | Test reports, test program | 待申请 |  | Not started | Не началась
NUC900 BSP PATCH Submit | Submit all the Linux BSP thread patch to linux | All participants | NUC900@googlegroups.com | In progress, submitted at any time | Не началась
NUC93X BSP developing | Submit NUC93X series BSP, and nuc900 series because there are too many different, resulting in early patch has not been accepted and now single for the series to create a new mach-nuc93x | 万宗顺 | mcuos.com@gmail.com | In progress, only the kernel and not driven uart | Не началась
Add your own ---- | If the list of projects which do not take responsibility for you